# STATEMENT OF WORK NO. 3

ERP Data Migration and Cutover Support — Project Kestrel

This Statement of Work No. 3 (this "SOW") is entered into as of May 4, 2026 by Bramwell & Cho Advisory LLP ("Consultant") and Pinewood Beverage Company, Inc. ("Client") under and subject to the Master Consulting Agreement between the parties dated September 11, 2024 (the "MCA"). Capitalized terms not defined in this SOW have the meanings given in the MCA. In the event of conflict, the MCA controls unless this SOW expressly amends it by section reference.

| Engagement name | Project Kestrel — SAP ECC 6.0 to S/4HANA data migration and cutover support |
| --- | --- |
| Client sponsor | Rosa Delgado, VP Enterprise Applications |
| Consultant engagement lead | Nathan Cho, Partner, Enterprise Technology |
| Period of performance | May 18, 2026 through December 18, 2026 |
| Fee basis | Fixed fee by milestone: USD 486,500 plus expenses per Section 5 |

## 1. Scope of Services

### 1.1 Workstream A — Data Profiling and Cleansing

#### 1.1.1 Data Profiling

Consultant will profile the material master, customer master, vendor master, open purchase orders, open sales orders, and three (3) years of financial transaction history in Client's SAP ECC 6.0 production instance, and will deliver a data quality assessment identifying duplicate, incomplete, and orphaned records with severity ratings and recommended remediation owners.

#### 1.1.2 Cleansing Rules and Execution

Consultant will define de-duplication and enrichment rules in Syniti ADM, execute cleansing in up to three (3) iterative cycles against the staging environment, and track defect burn-down to a target of no more than 0.5% residual critical defects at the final cycle.

### 1.2 Workstream B — Migration Build and Test

#### 1.2.1 Extraction and Transformation

Consultant will build extraction and transformation logic for the twenty-two (22) data objects listed in Appendix 1 using the SAP Migration Cockpit and custom ABAP where object complexity requires it, with unit test evidence retained in Client's Jira instance under project key KES.

#### 1.2.2 Mock Loads

Consultant will execute three (3) full-volume mock loads into the S/4HANA quality environment, publish reconciliation reports within two (2) business days of each mock load, and achieve a load success rate of at least 99.7% by record count at Mock Load 3.

### 1.3 Workstream C — Cutover and Hypercare

1.3.1 Consultant will prepare the cutover runbook (target duration not to exceed 72 hours of production downtime), staff the cutover command center during the go-live weekend of November 13–15, 2026, and provide hypercare support for four (4) weeks post go-live with a dedicated defect triage lead.

1.3.2 Out of scope: functional configuration of S/4HANA modules, custom code remediation outside migration objects, end-user training delivery, infrastructure sizing, and any services for Client's Canadian subsidiary. Changes to scope require a change order under Section 4.3 of the MCA.

## 2. Deliverables and Acceptance

2.1 Consultant will provide the deliverables listed below. Client will accept or reject each deliverable in writing within ten (10) business days of receipt, identifying material non-conformities with the applicable acceptance criteria. Deliverables not rejected within that period are deemed accepted. Consultant will have ten (10) business days to remediate and resubmit rejected deliverables.

| ID | Deliverable | Acceptance Criteria | Due Date |
| --- | --- | --- | --- |
| D1 | Data quality assessment report | Covers all six object domains; severity model agreed with sponsor | Jun 12, 2026 |
| D2 | Cleansing rulebook and cycle 3 results | Residual critical defects ≤ 0.5% of profiled records | Aug 7, 2026 |
| D3 | Migration build pack (22 objects) | Unit test evidence in Jira for each object; peer review sign-off | Sep 4, 2026 |
| D4 | Mock Load 3 reconciliation report | Load success ≥ 99.7% by record count; variances dispositioned | Oct 23, 2026 |
| D5 | Cutover runbook v1.0 | Dry-run executed; downtime plan ≤ 72 hours; rollback documented | Nov 6, 2026 |
| D6 | Hypercare exit report | No open Severity 1 defects; knowledge transfer sessions complete | Dec 18, 2026 |

## 3. Milestones and Fees

3.1 Fees are fixed by milestone and invoiced upon Client's acceptance of the associated deliverable. Payment terms are net thirty (30) days per Section 6.2 of the MCA.

| M# | Milestone | Linked Deliverable | Target Date | Fee (USD) |
| --- | --- | --- | --- | --- |
| M1 | Engagement mobilization and profiling complete | D1 | Jun 12, 2026 | 58,500 |
| M2 | Cleansing cycle 3 complete | D2 | Aug 7, 2026 | 72,000 |
| M3 | Migration build complete | D3 | Sep 4, 2026 | 98,000 |
| M4 | Mock Load 3 accepted | D4 | Oct 23, 2026 | 104,000 |
| M5 | Go-live cutover executed | D5 | Nov 16, 2026 | 96,000 |
| M6 | Hypercare exit accepted | D6 | Dec 18, 2026 | 58,000 |
| Total fixed fees |  |  |  | 486,500 |

## 4. Rate Card for Change Orders

4.1 Services added by change order will be charged at the blended rates below, which remain firm through December 31, 2026. Rates are quoted per hour in USD, exclusive of taxes and expenses.

| Role | Onshore | Nearshore | Offshore | Overtime Uplift | Weekend Uplift |
| --- | --- | --- | --- | --- | --- |
| Partner | 495 | — | — | n/a | n/a |
| Engagement Manager | 340 | 265 | — | +15% | +25% |
| Senior Data Architect | 310 | 245 | 175 | +15% | +25% |
| Migration Developer | 255 | 195 | 135 | +15% | +25% |
| Test Analyst | 205 | 160 | 110 | +15% | +25% |
| Cutover Coordinator | 230 | 180 | — | +15% | +25% |

## 5. Expenses

5.1 Client will reimburse reasonable, pre-approved travel and lodging expenses at cost, capped at eight percent (8%) of total fixed fees, invoiced monthly with receipts for any item over USD 25. Airfare above economy class and alcohol are not reimbursable.

## 6. Client Obligations and Assumptions

6.1 The fees and timeline in this SOW are based on the following assumptions. If an assumption proves materially inaccurate, the parties will process an equitable adjustment through the change order process:

- Client provides Consultant with remote VPN access and appropriately provisioned SAP user accounts within five (5) business days of the SOW effective date;

- Client makes data stewards for each object domain available for up to ten (10) hours per week during cleansing cycles;

- the S/4HANA quality environment is available and refreshed from production no later than July 6, 2026;

- Client's system integrator remains responsible for functional configuration and completes dependent configuration no later than August 21, 2026;

- the go-live date of November 15, 2026 will not move by more than one calendar week without a change order; and

- Client holds all licenses required for Syniti ADM and the SAP Migration Cockpit.

## 7. Key Personnel

7.1 Nathan Cho (Partner) and Ingrid Steensen (Senior Data Architect) are Key Personnel. Consultant will not reassign Key Personnel before Milestone M4 without Client's prior written consent, not to be unreasonably withheld, and will provide replacements of substantially equivalent qualification at no additional cost for ramp-up time.

## 8. Acceptance

By signing below, each party agrees to the terms of this SOW as of the date first written above. This SOW may be executed in counterparts, including by electronic signature.

| PINEWOOD BEVERAGE COMPANY, INC. | BRAMWELL & CHO ADVISORY LLP |
| --- | --- |
| By: _____________________________ | By: _____________________________ |
| Name: Rosa Delgado | Name: Nathan Cho |
| Title: VP Enterprise Applications | Title: Partner |
| Date: ___________________________ | Date: ___________________________ |