## Remediation
Asteron Group — 2026 Compliance Remediation
Internal audit and regulatory findings · Updated 2026-07-14 · Compliance PMO
Finding | Remediation Item | Due | Owner | Status | Done
F-2514 | Vendor due diligence | 2026-07-22 | SN | In Progress | 75%
F-2517 | Dormant admin IDs | 2026-07-31 | MK | Validation | 90%
F-2521 | Retention schedule | 2026-08-14 | AL | In Progress | 55%
F-2524 | PCI scan evidence | 2026-07-18 | JR | Overdue | 65%
F-2528 | Export screening log | 2026-08-28 | SN | Not Started | 0%
F-2530 | Privacy request SLA | 2026-07-25 | AL | Blocked | 40%
F-2533 | SOC report review | 2026-09-04 | MK | In Progress | 30%
F-2535 | Gift register attest | 2026-08-07 | DP | Validation | 95%
F-2539 | MFA break-glass test | 2026-07-29 | JR | In Progress | 70%
F-2542 | Policy exceptions | 2026-09-18 | DP | Not Started | 10%
F-2546 | Sanctions escalation | 2026-08-21 | SN | In Progress | 60%
F-2549 | Payroll access review | 2026-07-20 | MK | Overdue | 80%
F-2551 | Incident drill actions | 2026-08-11 | JR | Validation | 85%
F-2554 | Consent inventory | 2026-10-02 | AL | In Progress | 35%
F-2558 | Hotline case aging | 2026-08-04 | DP | Blocked | 45%
F-2560 | Third-party clauses | 2026-09-11 | SN | Not Started | 15%
F-2563 | SOX key reports | 2026-07-24 | MK | Closed | 100%
F-2566 | Training exceptions | 2026-08-17 | DP | In Progress | 50%
F-2569 | Encryption inventory | 2026-09-25 | JR | Not Started | 5%
F-2572 | Records legal hold | 2026-08-31 | AL | In Progress | 62%
F-2575 | Dealer audit files | 2026-10-16 | SN | Not Started | 0%
F-2578 | Segregation conflict | 2026-07-27 | MK | Validation | 92%
F-2581 | Breach notice tree | 2026-08-24 | AL | In Progress | 58%
F-2584 | Code of conduct ack | 2026-07-17 | DP | Closed | 100%
F-2587 | Cloud DPA register | 2026-09-08 | JR | Blocked | 25%