## Project Plan
Helios Manufacturing Group — Atlas ERP Implementation: Integrated Project Plan
Status week ending 2026-07-10 · PMO owner: P. Whitfield · Go-live target: 2026-11-16 · Gate next up: G3 Build Complete (24-Aug)
ID | Phase / Workstream | Task | Owner | Start | Finish | Dur (d) | % Complete | Status | Notes
ATL-001 | Phase 0 — Mobilization | Execute SOW and confirm steering committee charter | L. Okafor | 2026-02-02 | 2026-02-06 | 5 | 100% | Complete | Charter signed 06-Feb
ATL-002 | Phase 0 — Mobilization | Stand up project workspace, RAID log, and status cadence | P. Whitfield | 2026-02-04 | 2026-02-10 | 5 | 100% | Complete
ATL-003 | Phase 0 — Mobilization | Onboard systems integrator core team (8 FTE) | L. Okafor | 2026-02-09 | 2026-02-20 | 10 | 100% | Complete | 2 backfills closed late
ATL-004 | Phase 0 — Mobilization | Provision DEV / QA / STAGE tenants | R. Vasquez | 2026-02-16 | 2026-02-27 | 10 | 100% | Complete
ATL-005 | Phase 0 — Mobilization | Baseline current-state process inventory (L2) | M. Deshmukh | 2026-02-16 | 2026-03-06 | 15 | 100% | Complete | 142 processes catalogued
ATL-006 | Phase 1 — Discovery & Design | Order-to-cash design workshops (5 sessions) | M. Deshmukh | 2026-03-09 | 2026-03-27 | 15 | 100% | Complete
ATL-007 | Phase 1 — Discovery & Design | Procure-to-pay design workshops (4 sessions) | M. Deshmukh | 2026-03-16 | 2026-04-03 | 15 | 100% | Complete
ATL-008 | Phase 1 — Discovery & Design | Record-to-report design workshops (4 sessions) | K. Braun | 2026-03-23 | 2026-04-10 | 15 | 100% | Complete
ATL-009 | Phase 1 — Discovery & Design | Plan-to-produce design workshops (6 sessions) | S. Iyer | 2026-03-23 | 2026-04-17 | 20 | 100% | Complete | Shop-floor scope expanded
ATL-010 | Phase 1 — Discovery & Design | Chart of accounts redesign and mapping | K. Braun | 2026-04-06 | 2026-04-24 | 15 | 100% | Complete | Reduced 1,180 to 410 accounts
ATL-011 | Phase 1 — Discovery & Design | Item master and BOM data model definition | S. Iyer | 2026-04-13 | 2026-05-01 | 15 | 100% | Complete
ATL-012 | Phase 1 — Discovery & Design | Fit/gap analysis and RICEF inventory sign-off | M. Deshmukh | 2026-04-20 | 2026-05-08 | 15 | 100% | Complete | 38 RICEF objects approved
ATL-013 | Phase 1 — Discovery & Design | Security role design (SoD matrix) | T. Nakamura | 2026-04-27 | 2026-05-15 | 15 | 100% | Complete
ATL-014 | Phase 1 — Discovery & Design | Solution design document approval gate (G2) | L. Okafor | 2026-05-18 | 2026-05-22 | 5 | 100% | Complete | Approved with 3 conditions
ATL-015 | Phase 1 — Discovery & Design | Design-phase change requests disposition (CR-001..CR-007) | P. Whitfield | 2026-05-18 | 2026-05-29 | 10 | 100% | Complete | CR-005 deferred to R2
ATL-016 | Phase 2 — Build & Configure | Core financials configuration (GL, AP, AR, FA) | K. Braun | 2026-05-25 | 2026-07-03 | 30 | 85% | In Progress | AR dunning rules remaining
ATL-017 | Phase 2 — Build & Configure | Supply chain configuration (inventory, WMS-lite) | S. Iyer | 2026-06-01 | 2026-07-10 | 30 | 70% | In Progress
ATL-018 | Phase 2 — Build & Configure | Manufacturing configuration (routings, work centers) | S. Iyer | 2026-06-08 | 2026-07-17 | 30 | 60% | In Progress
ATL-019 | Phase 2 — Build & Configure | RICEF build wave 1 — 14 reports | R. Vasquez | 2026-06-01 | 2026-07-10 | 30 | 75% | In Progress | 11 of 14 in unit test
ATL-020 | Phase 2 — Build & Configure | RICEF build wave 2 — 9 interfaces | R. Vasquez | 2026-06-15 | 2026-07-31 | 35 | 40% | At Risk | EDI 856 mapping behind by 6 days
ATL-021 | Phase 2 — Build & Configure | RICEF build wave 3 — 8 enhancements | R. Vasquez | 2026-06-29 | 2026-08-07 | 30 | 20% | In Progress
ATL-022 | Phase 2 — Build & Configure | Pricing engine configuration and contract price import | M. Deshmukh | 2026-06-15 | 2026-07-24 | 30 | 55% | In Progress
ATL-023 | Phase 2 — Build & Configure | Tax engine integration (Vertex O Series) | K. Braun | 2026-06-22 | 2026-07-24 | 25 | 30% | At Risk | Vendor SOW amendment pending
ATL-024 | Phase 2 — Build & Configure | Bank connectivity and payment file formats (3 banks) | K. Braun | 2026-06-29 | 2026-08-07 | 30 | 25% | In Progress
ATL-025 | Phase 2 — Build & Configure | Output management — invoice, PO, pick list forms | R. Vasquez | 2026-07-06 | 2026-08-14 | 30 | 10% | In Progress
ATL-026 | Phase 2 — Build & Configure | Security roles build and unit test (61 roles) | T. Nakamura | 2026-07-06 | 2026-08-21 | 35 | 15% | In Progress
ATL-027 | Phase 2 — Build & Configure | Build-complete quality gate (G3) | L. Okafor | 2026-08-24 | 2026-08-28 | 5 | 0% | Not Started
ATL-028 | Phase 3 — Data Migration | Data cleansing — customer master (18,400 records) | A. Fontaine | 2026-05-25 | 2026-07-03 | 30 | 90% | In Progress | Duplicate merge at 96%
ATL-029 | Phase 3 — Data Migration | Data cleansing — vendor master (6,150 records) | A. Fontaine | 2026-06-08 | 2026-07-10 | 25 | 80% | In Progress
ATL-030 | Phase 3 — Data Migration | Data cleansing — item master and BOMs (44,000 SKUs) | A. Fontaine | 2026-06-08 | 2026-07-31 | 40 | 50% | At Risk | Legacy UoM conflicts on 2,100 SKUs
ATL-031 | Phase 3 — Data Migration | ETL build — master data objects (12 pipelines) | R. Vasquez | 2026-06-22 | 2026-07-31 | 30 | 45% | In Progress
ATL-032 | Phase 3 — Data Migration | ETL build — open transactions (SO, PO, AR, AP) | R. Vasquez | 2026-07-06 | 2026-08-14 | 30 | 20% | In Progress
ATL-033 | Phase 3 — Data Migration | Mock conversion 1 and reconciliation report | A. Fontaine | 2026-08-03 | 2026-08-14 | 10 | 0% | Not Started | Entry gated on ETL wave 1
ATL-034 | Phase 3 — Data Migration | Mock conversion 2 and reconciliation report | A. Fontaine | 2026-09-07 | 2026-09-18 | 10 | 0% | Not Started
ATL-035 | Phase 3 — Data Migration | Mock conversion 3 (dress rehearsal data set) | A. Fontaine | 2026-10-12 | 2026-10-16 | 5 | 0% | Not Started
ATL-036 | Phase 4 — Integration | Interface contract sign-off with 3PL (WMS) | S. Iyer | 2026-06-15 | 2026-06-26 | 10 | 100% | Complete
ATL-037 | Phase 4 — Integration | 3PL inbound/outbound interface build (4 flows) | R. Vasquez | 2026-06-29 | 2026-08-07 | 30 | 35% | In Progress
ATL-038 | Phase 4 — Integration | CRM bidirectional sync (accounts, orders, invoices) | R. Vasquez | 2026-07-06 | 2026-08-14 | 30 | 25% | In Progress
ATL-039 | Phase 4 — Integration | EDI trading partner migration (22 partners) | M. Deshmukh | 2026-07-13 | 2026-09-04 | 40 | 10% | At Risk | Top-5 partner test slots not confirmed
ATL-040 | Phase 4 — Integration | Payroll GL posting interface | K. Braun | 2026-07-20 | 2026-08-14 | 20 | 0% | Not Started
ATL-041 | Phase 4 — Integration | MES shop-floor confirmation interface | S. Iyer | 2026-07-27 | 2026-09-04 | 30 | 0% | Blocked | MES vendor API license unresolved
ATL-042 | Phase 4 — Integration | Integration test environment smoke pass | T. Nakamura | 2026-09-07 | 2026-09-11 | 5 | 0% | Not Started
ATL-043 | Phase 5 — Testing | Test strategy and entry/exit criteria approval | T. Nakamura | 2026-06-22 | 2026-07-03 | 10 | 100% | Complete
ATL-044 | Phase 5 — Testing | SIT cycle 1 — 480 scripted cases | T. Nakamura | 2026-08-17 | 2026-09-11 | 20 | 0% | Not Started
ATL-045 | Phase 5 — Testing | SIT cycle 2 — regression plus defect retest | T. Nakamura | 2026-09-14 | 2026-10-02 | 15 | 0% | Not Started
ATL-046 | Phase 5 — Testing | Performance test — month-end close and MRP run | R. Vasquez | 2026-09-21 | 2026-10-02 | 10 | 0% | Not Started
ATL-047 | Phase 5 — Testing | UAT — 62 business testers across 4 sites | P. Whitfield | 2026-10-05 | 2026-10-23 | 15 | 0% | Not Started | Backfill plan due 21-Aug
ATL-048 | Phase 5 — Testing | Security and SoD validation testing | T. Nakamura | 2026-10-05 | 2026-10-16 | 10 | 0% | Not Started
ATL-049 | Phase 5 — Testing | Defect burn-down to exit criteria (0 Sev1, ≤5 Sev2) | T. Nakamura | 2026-10-19 | 2026-10-30 | 10 | 0% | Not Started
ATL-050 | Phase 5 — Testing | UAT sign-off gate (G4) | L. Okafor | 2026-10-28 | 2026-10-30 | 3 | 0% | Not Started
ATL-051 | Phase 6 — Training & OCM | Change impact assessment by role (410 impacted users) | P. Whitfield | 2026-06-29 | 2026-07-24 | 20 | 65% | In Progress
ATL-052 | Phase 6 — Training & OCM | Training curriculum and materials build (28 courses) | P. Whitfield | 2026-07-27 | 2026-09-18 | 40 | 5% | In Progress
ATL-053 | Phase 6 — Training & OCM | Train-the-trainer certification (14 super users) | P. Whitfield | 2026-09-21 | 2026-10-02 | 10 | 0% | Not Started
ATL-054 | Phase 6 — Training & OCM | End-user training delivery — all sites | P. Whitfield | 2026-10-05 | 2026-11-06 | 25 | 0% | Not Started
ATL-055 | Phase 6 — Training & OCM | Site readiness assessments (Duluth, Reno, Monterrey) | P. Whitfield | 2026-10-19 | 2026-11-06 | 15 | 0% | Not Started
ATL-056 | Phase 7 — Cutover & Hypercare | Cutover runbook v1 (task-level, timed) | L. Okafor | 2026-09-14 | 2026-10-09 | 20 | 0% | Not Started
ATL-057 | Phase 7 — Cutover & Hypercare | Cutover dress rehearsal (48-hour clock) | L. Okafor | 2026-10-26 | 2026-10-28 | 3 | 0% | Not Started
ATL-058 | Phase 7 — Cutover & Hypercare | Go/no-go decision gate (G5) | Steering Cmte | 2026-11-09 | 2026-11-09 | 1 | 0% | Not Started
ATL-059 | Phase 7 — Cutover & Hypercare | Production cutover weekend execution | L. Okafor | 2026-11-13 | 2026-11-15 | 3 | 0% | Not Started | Freeze window agreed with ops
ATL-060 | Phase 7 — Cutover & Hypercare | Hypercare wave 1 (weeks 1–2, war room) | M. Deshmukh | 2026-11-16 | 2026-11-27 | 10 | 0% | Not Started
ATL-061 | Phase 7 — Cutover & Hypercare | Hypercare exit and transition to AMS (G6) | L. Okafor | 2026-12-14 | 2026-12-18 | 5 | 0% | Not Started